## TTS en
Safe Job Analysis (SJA)
Safe Job Analysis (SJA, Finnish: Työn turvallisuussuunnitelma, TTS) is used to remove obstacles to safe work, such as the inadequate hazard identification or a lack of awareness amongst personnel concerning safe working methods. It is the responsibility of the foreman to ensure that the plan is made together with employees for each new task scheduled in the site weekly work plan and separately for each high-risk activity.
A plan made by a subcontractor must be checked and approved by a Skanska foreman who will keep a copy of the plan. A method statement or similar plan dealing with hazards may replace SJA.
Project / contract | [8 empty] | Site number
Work covered by the SJA | [8 empty] | SJA made (date)
Does the work require detailed planning in accordance with Safety Standards? | [8 empty] | Work carried out by (company)
Please refer to the Skanska standard if work concerns one of the following:
| Work at height |  |  |  | Excavations |  |  |  | SJA made by
| Confined spaces (subfloor, container, tunnel etc.) |  |  |  | Lifting work (high-risk lifting)
| Work near services (gas, water, electric, etc) |  |  |  | Temporary works
| Dusty work (observe the dust control plan) |  |  |  | Vibration at work
Parties exposed to work hazards in addition to workgroup and foremen
| Other personnel, third party |  |  |  | Temporary workers, interns etc.
Personal Protective Equipment | [8 empty] | Consider in riskmanagement
| Eye protection, type: |  |  |  | Use of chain saw (cut resistant gear) |  |  |  |  | Language differences and communication
| Gloves, type: |  |  |  | Personal fall arrest system |  |  |  |  | Personal characteristics such as age, experience, competence, pregnancy
| Respiratory protection, type: |  |  |  | Other, what:
| Hearing protection: |  |  |  | Work platform is safe and suitable for the job. |  |  |  |  | Health restrictions
Fire resistant clothing:
1. What tasks does job include? |  |  |  | 2. Task hazards |  |  |  | 3. How will the risks be controlled?
Job Hazards (write the relevant number in the table above)
1 | Noise |  | 8 | Moving vehicles, cranes |  |  |  | 15 | Manual handling
2 | Vibration |  | 9 | Trapped, being caught on, hit |  |  |  | 16 | Working postures
3 | Chemicals, fuels, gases, di-isocyanate |  | 10 | Falling, falling objects |  |  |  | 17 | Pressure to get job done
4 | Mould, bacteria, PAH |  | 11 | Tripping, slipping |  |  |  | 18 | Difficult weather conditions
5 | Airborne particles, sparks |  | 12 | Slicing, cutting, abrasion |  |  |  | 19 | Other contractors / coordination
6 | Dust, quartz dust, hardwood dust |  | 13 | Collapse |  |  |  | 20 | Lighting
7 | Closed space, air quality |  | 14 | Electrocution |  |  |  | 21 | Other, eg. drowning
Conditions for starting the work Are there some special things that need to be coordinated before the work can be started (general or work site lighting, access to the work site, etc.)
Waste fractions generated at work
Waste fraction |  | Container |  | Waste fraction |  |  | Container |  | Waste fraction |  | Container
| Asphalt |  |  |  | Hard plastic |  |  |  |  | Recycled wood
| Concrete and bricks |  |  |  | Metal |  |  |  |  | Wood pallets
| Bitumen |  |  |  | Glass |  |  |  |  | Aerosol
| Plastic insulation (EPS,XPS) |  |  |  | Plasterboard/ Gypsum |  |  |  |  | Hazardous waste
| Insulation/mineral wool |  |  |  | Cardboard |  |  |  |  | Energy waste
| Plastic film |  |  |  | Wood
Commitment to Safe Work All SJA parties are responsible for the safe execution of this job. The foreman is responsble for ensuring that the actions agreed in this plan are discussed with new personnel. A plan made by a subcontractor will be checked and approved by a Skanska foreman who will keep a copy of the plan.
Signature |  | Company |  |  |  | Signature |  |  |  | Company
1. | [5 empty] | 7.
2. | [5 empty] | 8.
3. | [5 empty] | 9.
4. | [5 empty] | 10.
5. | [5 empty] | 11.
6. | [5 empty] | 12.
Special qualifications related safety
Qualification |  | Person (the signature number) |  |  |  | Qualification |  |  |  | Person (the signature number)
Temporary Works Safety
To be filled in case of temporary works (TWs). TWs are needed to enable the permanent works to be built. Usually the TWs are removed after use - e.g. scaffolds, props, shoring, excavation support, falsework to support slabs / walls and formwork for in-situ concrete constructions, working platforms for heavy mobile equipment including cranes and piling rigs.
The Skanska foreman responsible for the work activity will check and confirm sections 1- 4 as work progresses.
Temporary structure/structures used during the work phase
1. Materials approved for temporary works | [5 empty] | 2. Installation complies with design / permit to load (load test if necessary)
Date, signature and name in print | [5 empty] | Date, signature and name in print
3. Monitoring the condition when in use under load (mark if the inspection is not carried out in weekly site inspection) | [5 empty] | 4. Permit for the dismantling of the temporary works
Date, signature and name in print | [5 empty] | Date, signature and name in print
Päivämäärä ja allekirjoitus
Skanska foremens' signatures and names in print | [8 empty] | Telephone
3. How the risks will be controlled?
Then think how each of the hazards can be managed.
If possible, remove the hazard. If it cannot be removed chose safer alternative or limit exposure. If these are not possible, safety is ensured with technical protective devices (isolation of the danger area, fall protection rails...). Finally, if nothing else works, use the personal protective equipment (in addition to mandatory protective equipment).
Care, caution and safe work are included in everything we do. These have to be communicated but they are not controls. Instead, write here the exact things that make the operation safe, such as checking the lifting devices before each lift, monitoring the condition of the machines, communication methods with others working nearby, following the planned excavation levels, using barriers to restrict the work areas, following the access routes, keeping up order and tidyness etc.
It is good to remember the lessons learned from the accidents that have happened and think about what can unexpectedly go wrong in this work.
2. Task hazard
Think for each work task what hazards involves in the task. Use the list of hazards.
It is good to note that from January 1, 2024, the risk of falling must be prevented from a height of 1.5 meters.
1. What tasks does job include?
Divide the job into tasks, starting with preparatory tasks (such as logistics) and ending with cleaning the work area. Write tasks on their own lines. Choose tasks so that there are rather too many tasks than too few. It is easier to identify risks in smaller tasks.
You can write on one line the things that have to be considered throughout the work, e.g. surrounding traffic. You can add lines to the form if necessary.
Work that requires extended planning in accordance with Safety Standards
The global standards of Skanska defines the way to operate in certain jobs. The requirements are included in the online courses in finnish.
Personal protective equipment used at work
What special personal protective equipment is needed in addition to mandatory protective equipment?
Eye protection can be a visor that covers the face, goggles that fit tightly on the face, or protection class B (e.g. when using a bolt gun).
Remember e.g. chemical gloves, fresh air mask or half mask when working with dust.
Knowing how to use personal fall arrest system and taking care of annual inspections must be ensured. The anchor points for the fall arrest system must be guided.
The requirements for the work platforms are presented in the Skanska-pakka.
Special qualifications related safety
Check and write down the special qualifications required, if this has not been done during the site induction. The certificates are checked and copied/photographed before the work starts.
Special qualifications don't mean basic qualifications like occupational safety card or road safety trainings, but for example:
Employer's permission to secure a load, use a personal lift or drive a forklift
Di-isocyanate usage training
Scaffolding qualification
Water hygiene card
Qualifications related to blasting and track work
Diver qualification
Crane operator qualification
Rope work qualification
Waste fractions and collection containers generated at job
The waste fraction must be collected separately if it is generated at least 5 kg per week at the construction site
Ensuring the safety of temporary works
A temporary works is a structure that is needed during construction, but which removed after use. Failure of temporary works can cause the permanent structure to collapse, resulting in serious injury or death. Therefore, careful planning and use of temporary works is important.
Conditions for starting the job
If there are some special things that need to be coordinated before the safe start write them here (e.g. lighting, state of the work phase, arrangements required by the job, such as scaffolding, etc.)
Instructions and clarifications